## Sheet1
[6 empty] | Date of evaluation: | 2016-08-31
Follow-up evaluation:
[6 empty] | Date Issued to OEMS: | 2016-09-26
IEQ Dashboard
Location: | Barry Elementary School (K-8) |  |  | KEM Project Number: | K1100
Requested by: | PFT |  |  | Year Built/Stories: | 2008/3 | Objective: Conduct IEQ Evaluation with PFT Representative
ULCS#: | 1200 - 5900 Race Street
BE:
FAC: | Tim Holman (tjholman) |  |  | PFT Present: | Jerry Roseman
Principal: | Derrick Hardy (drhardy) |  |  | PFT Building Rep.: | N/A
Location (Room/Area) | Findings | Quantity | Category | Corrective Action | Trade | Start Date | End Date
Gym Office | Water stained and missing ceiling tiles were observed. No signs of active leaks were observed above the suspended ceiling. | 4 EA | Mold/Moisture | The impacted ceiling tiles should be replaced and monitored. New staining should be reported for further evaluation as needed. | Building Engineer
2nd Floor Hallway (Race Street) | Water stained and missing ceiling tiles were observed. No signs of active leaks were observed above the suspended ceiling. | 4 EA | Mold/Moisture | The impacted ceiling tiles should be replaced and monitored. New staining should be reported for further evaluation as needed. | Building Engineer
Room 214 | Water staining was observed on the ceiling tiles and wallboard. | 1 EA | Mold/Moisture | The impacted ceiling tiles should be replaced and the stained wallboard painted. New staining should be reported for further evaluation as needed. | Building Engineer
2nd Floor Hallway | The light trim was hanging below the ceiling. | 2 EA | Safety | The light trim should be secured to ceiling. | Building Engineer
Room 107 | Water stained and missing ceiling tiles were observed. Ceiling tile debris was observed in the light cover. The source of moisture was from spills in the custodial closet on the floor above. | 4 EA | Mold/Moisture | The impacted ceiling tiles should be replaced and the light cover cleaned. | Building Engineer
Room 108 | A ceiling tile was missing from a plumbing repair. The water supply lines were repaired, however the lines were not insulated. | 4 LF | Mold/Moisture | The water supply lines should be insulated to prevent condensation and the ceiling tile should be replaced. | Building Engineer
Room 109 | Particulate accumulation was observed on the relief grilles | 4 EA | Point Source | The particulate accumulation should be removed from the relief grille. | Building Engineer
Room 109 | A water stained ceiling tile was observed. No signs of active leaks were observed. | 1 EA | Mold/Moisture | The impacted ceiling tile should be replaced and monitored. New staining should be reported for further evaluation as needed. | Building Engineer