## Sheet1
[6 empty] | Date of evaluation: | 2016-09-29
Follow-up evaluation:
Date Issued to OEMS:
IEQ Dashboard
Location: | A.S. Jenks Elementary School (K-5) |  |  | KEM Project Number: | K1100
Requested by: | PFT |  |  | Year Built/Stories: | 1897/3 | Objective: Conduct evaluation following reported occupant concerns
ULCS#: | 2520- 2501 S. 13th St.
BE: | Andrew Lacquintano
FAC: | Steve Manna |  |  | PFT Present: | Jerry Roseman
Principal: | Siouda Douglas |  |  | PFT Building Rep.: | Maria Greco
Location (Room/Area) | Findings | Quantity | Category | Corrective Action | Trade | Start Date | End Date
Room 106 | Moisture damaged paint and plaster was observed around the windows. | 45 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Room 106 | Paint and plaster debris was observed on a few of the window sills. | N/A | Point Source | The window sills should be cleaned with a damp cloth on a daily basis. | Building Engineer
Room 104 | Efflorescence was observed above 2 windows. | 10 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Painting
Room 103 | Efflorescence was observed above the windows on the right side of the room. | 2 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Painting
Room 102 | Moisture damaged paint and plaster was observed around the windows. | 15 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
East Stairwell | Moisture damaged plaster and staining was observed from a roof leak that was stabilized. | 2 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Room 202 | Moisture damaged paint and plaster was observed around the windows and in the corner of the room. | 50 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Room 202 | Paint and plaster debris was observed on a few of the window sills. | N/A | Point Source | The window sills should be cleaned with a damp cloth on a daily basis. | Building Engineer
Room 202 Closet | Staining and flaking paint was observed on the ceiling from a roof leak that was stabilized. | 4 SF | Point Source | The flaking paint should be removed in accordance with lead safe work practices. | Painting
Room 203 | Water staining was observed on the ceiling from a roof leak that was stabilized. | 20 SF | Point Source | The flaking paint should be removed in accordance with lead safe work practices. | Painting
Room 203 | Moisture damaged paint and plaster was observed around the windows on the right side of the room. | 50 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Hallway between Room 203 and 204 | Staining and flaking paint was observed on the ceiling from a roof leak that was stabilized. | 10 SF | Point Source | The flaking paint should be removed in accordance with lead safe work practices. | Painting
Room 204 | Moisture damaged plaster was observed around two of the windows. | 10 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Room 204 | Paint and plaster debris was observed on a couple window sills. | N/A | Point Source | The window sills should be cleaned with a damp cloth on a daily basis. | Building Engineer
Room 206 | Moisture damaged plaster was observed around two of the windows. | 20 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Room 206 | Paint and plaster debris was observed on a couple window sills. | N/A | Point Source | The window sills should be cleaned with a damp cloth on a daily basis. | Building Engineer
Room 207 | Moisture damaged paint and plaster was observed on the wall and ceiling from a roof leak that was stabilized. | 25 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Hallway outside Room 207 | Staining and flaking paint was observed on the ceiling from a roof leak that was stabilized. | 10 SF | Point Source | The flaking paint should be removed in accordance with lead safe work practices. | Painting
Counselor's Office | Moisture damaged plaster was observed on a section of the upper wall. | 20 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting
Nurse's Office | Flaking paint was observed above the window. | 2 SF | Point Source | The flaking paint should be removed in accordance with lead safe work practices. | Painting
Room 201 | An active roof leak was observed by the entrance. | 1 EA | Mold/Moisture | The roof above room 201 should be evaluated and repaired as needed. | Roofing
Room 201 | Staining and flaking paint was observed on the ceiling. | 45 SF | Point Source | The flaking paint should be removed in accordance with lead safe work practices. | Painting
Room 201 | Moisture damaged paint and plaster was observed around the windows on the east side of the room. | 15 SF | Point Source | The moisture damaged paint and plaster should be repaired in accordance with lead safe work practices. | Plastering/Painting