## Sheet1
[6 empty] | Date of evaluation: | 2016-12-13
Follow-up evaluation:
[6 empty] | Date Issued to OEMS: | 2016-12-13
IEQ Dashboard
Location: | Beeber High School (9-12) |  |  | KEM Project Number: | K1100
Requested by: | PFT |  |  | Year Built/Stories: | 1933/3 | Objective: Conduct IEQ assessment following the report of steam leaks
ULCS#: | 4100 - 5925 Malvern Avenue
BE: | Kenneth Mack (kmack)
FAC: | Richard Toohey (rmtoohey) |  |  | PFT Present: | Yes
Principal: | Khary Moody |  |  | PFT Building Rep.:
Location (Room/Area) | Findings | Quantity | Category | Corrective Action | Trade | Start Date | End Date
Main Entrance | A steam leak was observed on the east radiator in the main lobby. | 1 EA | Mold/Moisture | Repair the steam leak on the radiator in the main lobby. | Steam fitting
Room 101 | An asbestos containing pipe riser was observed in the corner of the room at the water damaged section of flooring. This insulation should be removed to allow for flooring repairs. | 12 LF | Point Source | An asbestos Design Data Collection (DDC) was issued on December 13, 2016 for the removal. | Environmental |  | Complete
Room 101 | Steam from a leak in the crawlspace has impacted a section of wood flooring in the corner of the room by the window. Elevated moisture content was detected on this section of flooring. | 40 SF | Mold/Moisture | The 5'x8' section of impacted flooring should be replaced following removal of the asbestos pipe insulation and steam leak repairs. | Carpentry
Room 101 | A steam leak in the crawlspace below this room was reported by the Building Engineer. | 1 EA | Mold/Moisture | Repair steam leak in crawlspace below room 101. | Steam fitting
Room 103 | A steam leak was observed on the radiator between rooms 103 A and 103 B. | 1 EA | Mold/Moisture | Repair stem leak on radiator. | Steam fitting
Room 103 | A section of flooring below the radiator was impacted by the steam leak. | 6 SF | Mold/Moisture | The 2'x3' section of hardwood flooring below the radiator should be replaced following repairs to the steam leak. | Steam fitting
Room 108 | A steam leak was observed on the radiator piping between the crawlspace and the radiator. No asbestos containing pipe insulation was observed on this line. | 1 EA | Mold/Moisture | Repair the steam leak on the supply line. | Steam fitting
Room 108 | The wooden baseboard behind the radiator was damaged by the steam leak. | 5 LF | Mold/Moisture | The wooden baseboard should be replaced following repairs to the steam leak. | Carpentry
1st Floor Hallway | The compressor on the hydration station was making a very loud noise and was unplugged. | 1 EA | Point Source | Repair the compressor on the 1st floor hydration station. | Plumbing |  | Complete